## Sheet1
Day | Date | Files_Worked | Status | Description
Friday | 2025-08-08 | Writtern required Entities | Done | Categories, Product, User, Supplier, Transactions
Saturday | 2025-08-09 | Done DTO and repo | Done | DTO for Encaps, and repo for search functionality
Sunday | 2025-08-10 | Break | Done | Break
Monday | 2025-08-11 | Break | Done | Break
Tuesday | 2025-08-12 | Exceptions,Auth Users, Customer User Details,JWT Utils ,Auth Filter,Security FIlter | Done | All security files configured.
Wednesday | 2025-08-13
Thursday | 2025-08-14 | Specification Filter and user Service , Controller and test | Done | Implemented the user service functionality and tested API accordingly
Friday | 2025-08-15 | Category Service, Controller and text ¦ Supplier Service , controller&Test ¦ Product service controller and test | Done | Implemented the category service , supplier service and Product service
Saturday | 2025-08-16 | Transaction service controller and test + Back Log
Sunday | 2025-08-17 | revising all backend code . |  | break
Monday | 2025-08-18 | break
Tuesday | 2025-08-19 | Front end : Create Project , service layout and pagination + Frontend Auth
Wednesday | 2025-08-20 | Frontend : Admin Management Pages
Thursday | 2025-08-21 | Frontend : Admin Management Pages
Friday | 2025-08-22 | Front-End Manager's Page (Purchase , sales , transaction)
Saturday | 2025-08-23 | DashBoard pages and Profile Pages
Sunday | 2025-08-24
Monday | 2025-08-25
Tuesday | 2025-08-26
2025-08-27
2025-08-28
2025-08-29
2025-08-30
2025-08-31